## Slide 1
2015
2016
Today
Dec
2016
Feb
UI Prototype Model
12/25/2015
Environment Setup at UMBC (For e.g: Database setup etc.)
12/25/2015
End to End Testing
1/15/2016
Roll-out
1/18/2016
Questionnaire Document Finalization
12/11/2015
Computational Logic Model
12/18/2015
Server Side Implementation (For e.g: Node.js or PHP script development)
1/8/2016
eEnergy Deadline
2/12/2016
Description | Start Time | End Time
Questionnaire Document Finalization | 13-Nov-2015 | 11-Dec-2015
Computational Logic Model | 06-Nov-2015 | 18-Dec-2015
UI Prototype Development | 10-Nov-2015 | 25-Dec-2015
Environment Setup at UMBC | 14-Dec-2015 | 25-Dec-2015
Server Side Implementation | 28-Dec-2015 | 08-Jan-2016
End to End Testing | 11-Jan-2016 | 15-Jan-2016
Roll-out | 18-Jan-2016 | 18-Jan-2016
Experiments on AMT | 19-Jan-2016 | 12-Feb-2016